## Sheet1
PERT Example - Widgetco section 8.4 - (project diagram in fig 31, p434)
Note that the table below only includes activities that are on the critical path:
from | to | a | b | m | E(T) | Var(T)
1 | 2 | 5 | 13 | 9 | 9 | 1.7778
2 | 3 | 0 | 0 | 0 | 0 | 0
3 | 4 | 1 | 13 | 7 | 7 | 4
4 | 5 | 8 | 12 | 10 | 10 | 0.44444
5 | 6 | 9 | 15 | 12 | 12 | 1
|  | Assume normal distn with |  |  | 38 | 7.2222
[5 empty] | mean | var
|  | Find P{finish by time x = 35} |  |  | 35
|  | P{<=x} = | 0.13214 | Probability of finishing on time